## Datos
NOMBRE DEL GRUPO | Acid Drops
NOMBRE DEL VIDEOJUEGO | God's Choice
NOMBRE DE LOS INTENGRANTES DEL GRUPO | Óscar Lleixà, Nacho Gan, Marc Cornellas & Raúl Herrera
CALENDARIO | Task List
METODOLOGIA | Discord/Drive/Trello/Github
ROLES | ENCARGADO DEL ROL
GAME DESINGER | Raúl Herrera
ART | Óscar Lleixà & Nacho Gan
PROGRAMMING | Marc Cornellas
VFX/LIGHTING | Raúl Herrera
AUDIO | Óscar Lleixà

## Task List
| TAREA | DESCRIPCIÓN | ASCENDENTE | FASE | RAMA | ASIGNADO A | ESTIMACIÓN | ENTREGA | ESTADO | OBSERVACIONES
GAME DESIGN DOCUMENT / PITCH DOCUMENT | Game Card |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Narrative |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Main Characteristics |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| References |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Types of Fun |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Types of Players |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Character Definition |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Camera Definition |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Control Definition |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Objetives Definition |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Gameplay |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Main Mechanics Definition |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
| Unique Selling Points |  |  | PRE-PRODUCTION | GAME DESIGN | RAÚL HERRERA |  | 2020-11-16 | IN PROCESS
0
ART 2D | Pinterest Visual |  |  | PRE-PRODUCTION | ART | NACHO GAN | 3h | 2020-11-16 | DONE
| Pinterest Characters |  |  | PRE-PRODUCTION | ART | NACHO GAN | 5h | 2020-11-16 | DONE
| Pinterest Props |  |  | PRE-PRODUCTION | ART | NACHO GAN | 2h | 2020-11-16 | DONE
| Pinterest Environment |  |  | PRE-PRODUCTION | ART | NACHO GAN | 5h | 2020-11-16 | DONE
| Moodboard Visual |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN | 2h | 2020-11-16 | DONE
| Moodboard Characters |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN | 4h | 2020-11-16 | DONE
| Moodboard Props |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN | 3h | 2020-11-16 | DONE
| Moodboard Environment |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN | 3h | 2020-11-16 | DONE
| Thumbsnails Player |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Thumbsnails Enemies |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Thumbsnails Environment |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Lineart Environment |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Lineart Enemies |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Lineart Player |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Color Player |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Color Enemies |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Final Concept Player |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Final Concept Enemies |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Final Concept Environment |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Mockup Gameplay |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Mockup Title |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Mockup Menu |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | 2020-11-16 | IN PROCESS
| Pixel Art Characters |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Pixel Art Enemies |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Pixel Art Props |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Pixel Art Environment |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Pixel Art Animations Character |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Pixel Art Animations Enemies |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Pixel Art Animations Environment |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Pixel Art Animations Interface |  |  | PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
1d 3h
UNITY | Mechanics Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Menus Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Interface Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Fights Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Gameplay Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| AI Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Map Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Levels Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Camera Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Pacing Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Decisions Prototype |  |  | PRE-PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | 2020-10-13 | IN PROCESS
| Implement Interface |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Menus |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Mechanics |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Characters Sprites |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Enemies Sprites |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Environment Sprites |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Interface Sprites |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Map Sprites |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement VFX |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Characters Sounds |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Enemies Sounds |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Environment Sounds |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Implement Interface Sounds |  |  | PRODUCTION | PROGRAMMING | MARC CORNELLAS |  | FALSE | TO DO
| Level Design |  |  | PRODUCTION | PROGRAMMING | NACHO GAN |  | FALSE | TO DO
0
INTERFACE | Diagrama de flujo |  |  | PRE-PRODUCTION | ART | MARC CORNELLAS |  | FALSE | TO DO
| Define Design |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Define Colors |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Define Interface |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| HUD |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Define Pause Menu |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Define Setting Interface |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Define Audio Interface |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
| Define Control Interface |  |  | PRE-PRODUCTION | ART | ÓSCAR LLEIXÀ & NACHO GAN |  | FALSE | TO DO
0
GAME DESIGN | Define Cards |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Cards Stats |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Player Stats |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Enemies Designs |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Enemies Stats |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Enemies Mechanics |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Items |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Interactables Characters |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Map |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Mock up First Level |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Mock up Second Level |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Enemies Loots |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Enemies Location |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Define Map Location |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Balancing Enemies |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Balancing Cards |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Balancing Player Stats |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Balancing Enemies Loots |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
| Balancing Items |  |  | PRODUCTION | GAME DESIGN | TODOS |  | FALSE | TO DO
0
AUDIO | Evaluate Sounds |  |  | PRE-PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | 2020-11-16 | TO DO
| Sound Feedback |  |  | PRE-PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | 2020-11-16 | TO DO
| Sound Breakdown & Definition |  |  | PRE-PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | 2020-11-16 | TO DO
| Music Definition |  |  | PRE-PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | 2020-11-16 | TO DO
| Player Sounds |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Characters Sounds |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Enemies Sounds |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Environment Sounds |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Map sound |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Interface Sounds |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Fights Sounds |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Menu Sounds |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Fights Music |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
| Music |  |  | PRODUCTION | AUDIO/VFX | ÓSCAR LLEIXÀ |  | FALSE | TO DO
0
VFX | VFX Player |  |  | PRODUCTION | AUDIO/VFX | RAÚL HERRERA |  | FALSE | TO DO
| VFX Characters |  |  | PRODUCTION | AUDIO/VFX | RAÚL HERRERA |  | FALSE | TO DO
| VFX Enemies |  |  | PRODUCTION | AUDIO/VFX | RAÚL HERRERA |  | FALSE | TO DO
| VFX Environment |  |  | PRODUCTION | AUDIO/VFX | RAÚL HERRERA |  | FALSE | TO DO
| VFX Map |  |  | PRODUCTION | AUDIO/VFX | RAÚL HERRERA |  | FALSE | TO DO
| Lightings |  |  | PRODUCTION | AUDIO/VFX | RAÚL HERRERA |  | FALSE | TO DO
0
OTHERS | Gantt Diagram & Cost Estimation |  |  | PRE-PRODUCTION | OTHER | NACHO GAN | 2h | 2020-10-18 | DONE
| Task List |  |  | PRE-PRODUCTION | OTHER | NACHO GAN | 3h | 2020-10-18 | DONE
| Producer |  |  | PRODUCTION | OTHER | NACHO GAN | 8 months | FALSE | IN PROCESS
| Community Manager |  |  | PRODUCTION | OTHER | ÓSCAR LLEIXÀ | 1 month 7 days | FALSE | TO DO
| English Translate |  |  | POST-PRODUCTION | OTHER | RAÚL HERRERA |  | FALSE | TO DO
9 month 7days 5h